## excel
/Non Project/PSP Fundamentals & Advanced/Program 5
PSP2.1 Project Plan Summary
Project Settings
Project Owner | Edgar Alexander Aguilar BolaÃ±os
Start Date | abr 04, 2017 08:08:42 AM
Completion Date | abr 05, 2017 03:12:29 PM |  |  |  | Completed: *
Keywords
Language | Java
Overall Metrics
Summary | Plan | Actual | To Date
Size/Hour | 32.5 | 33.2 | 33.6
Planned Time | 0.36736 |  | 1899-12-31 08:42
Actual Time |  | 0.38056 | 1899-12-31 12:27
CPI (Cost-Performance Index) |  |  | 0.9
% Reuse | 0% | 0% | 6.53%
% New Reusable | 0% | 0% | 0%
Test Defects/KLOC or equivalent | 15.2 | 23.1 | 17.1
Total Defects/KLOC or equivalent | 33.6 | 36.3 | 34.3
Yield % | 54.8% | 36.4% | 50%
Code Review Rate | 1159 | 1136 | 1185
% Appraisal COQ | 3.6% | 4.56% | 3.84%
% Failure COQ | 14.8% | 17.5% | 15.5%
COQ A/F Ratio | 0.24 | 0.26 | 0.25
PQI | 0 | 0 | 0
Program Size
| Plan | Actual | To Date
Base (B) | 0 | 0 | 342
Deleted (D) | 0 | 0 | 2
Modified (M) | 0 | 0 | 6
Added (A) | 287 | 303 | 1219
Reused (R) | 0 | 0 | 97
Added and Modified (A+M) | 287 | 303 | 1225
Total Size (T) | 287 | 303 | 1486
Total New Reusable | 0 | 0 | 0
Estimated Proxy Size (E) | 244 | 303 | 1209
Upper Prediction Interval (70%) | N/A
Lower Prediction Interval (70%) | N/A
Time In Phase
| Plan | Actual | To Date | To Date %
Planning | 0.093056 | 0.0625 | 0.35139 | 23.1%
Design | 0.052778 | 0.05625 | 0.22083 | 14.5%
Design Review | 0.0027778 | 0.00625 | 0.015278 | 1.01%
Code | 0.11111 | 0.15069 | 0.49583 | 32.6%
Code Review | 0.010417 | 0.011111 | 0.043056 | 2.83%
Compile | 0.00069444 | 0 | 0.0013889 | 0.09%
Test | 0.054167 | 0.066667 | 0.23403 | 15.4%
Postmortem | 0.041667 | 0.027083 | 0.15694 | 10.3%
Total | 0.36736 | 0.38056 | 1899-12-31 12:27
Total Time UPI (70%) | N/A
Total Time LPI (70%) | N/A
Defects Injected
| Plan | Actual | To Date | To Date %
Before Development | 0 | 0 | 0 | 0%
Planning | 0.62 | 0 | 2 | 4.76%
Design | 3.11 | 1 | 11 | 26.2%
Design Review | 0 | 0 | 0 | 0%
Code | 5.9 | 10 | 29 | 69%
Code Review | 0 | 0 | 0 | 0%
Compile | 0 | 0 | 0 | 0%
Test | 0 | 0 | 0 | 0%
Total | 9.63 | 11 | 42
Defects Removed
| Plan | Actual | To Date | To Date %
Planning | 0 | 0 | 0 | 0%
Design | 0.31 | 0 | 1 | 2.38%
Design Review | 0 | 0 | 0 | 0%
Code | 3.11 | 1 | 11 | 26.2%
Code Review | 1.86 | 3 | 9 | 21.4%
Compile | 0 | 0 | 0 | 0%
Test | 4.35 | 7 | 21 | 50%
Total | 9.63 | 11 | 42
After Development | 0 | 0 | 0
Defect Removal Efficiency
| Plan | Actual | To Date
Defects/Hour - Design Review | 0 | 0 | 0
Defects/Hour - Code Review | 7.54 | 11.2 | 8.71
Defects/Hour - Compile | 0 | #DIV/0! | 0
Defects/Hour - Test | 3.36 | 4.38 | 3.74
DRL (DLDR/UT) | 0 | 0 | 0
DRL (Code Review/UT) | 2.25 | 2.57 | 2.33
DRL (Compile/UT) | 0 | #DIV/0! | 0
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.
Report generated at 03:16 PM on 5/04/2017